## Sheet1
ITSC-3155 Software Engineering
Product Backlog
Feature Name | PRIORITY | POINTS | DEFINE USER STORY | ASSIGNED TO SPRINT | SPRINT #
User registration and guest checkout | High | 8 | Yes | Yes | 1
Menu management | High | 13 | Yes | Yes | 2
Order placement | High | 10 | Yes | Yes | 3
Payment processing | High | 15 | Yes | Yes | 4
Real time order tracking | High | 12 | Yes | Yes | 5
Order management for staff | High | 11 | Yes | Yes | 6
Rating system | Medium | 8 | Yes | Yes | 7
Promotion & Marketing | Medium | 10 | Yes | Yes | 8
Data analysis and report | Medium | 13 | Yes | Yes | 9
Documentation & training | Medium | 7 | Yes | Yes | 10
Customer support and help center | Low | 6 | Yes | No | -
-